{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["VDI"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":6,"defined_names":189,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"VDI","index":0,"n_rows":70,"n_cols":10,"rows_kept":70,"cut":false,"hidden":false,"merged":[[72,3,72,6],[73,3,73,6],[74,3,74,6],[75,3,75,6],[76,3,76,6],[77,3,77,6],[60,3,60,6],[61,3,61,6],[62,3,62,6],[63,3,63,6],[64,3,64,6],[65,3,65,6],[48,3,48,6],[49,3,49,6],[50,3,50,6],[51,3,51,6],[52,3,52,6],[53,3,53,6],[36,3,36,6],[37,3,37,6],[38,3,38,6],[39,3,39,6],[40,3,40,6],[41,3,41,6],[24,3,24,6],[25,3,25,6],[26,3,26,6],[27,3,27,6],[28,3,28,6],[29,3,29,6],[13,3,13,6],[14,3,14,6],[15,3,15,6],[16,3,16,6],[17,3,17,6],[18,3,18,6],[3,11,3,12],[4,3,4,6],[5,3,5,6],[6,3,6,6],[7,3,7,6],[8,3,8,6],[3,2,3,7],[1,2,1,7],[2,2,2,7],[0,2,0,7],[37,9,38,9],[39,9,48,9],[50,9,52,9],[54,9,58,9],[60,9,65,9],[69,9,70,9],[12,9,14,9],[15,9,17,9],[18,9,19,9],[20,9,26,9],[27,9,32,9],[35,9,36,9],[78,3,78,6],[79,3,79,6],[68,3,68,6],[69,3,69,6],[70,3,70,6],[71,3,71,6],[66,3,66,6],[67,3,67,6],[56,3,56,6],[57,3,57,6],[58,3,58,6],[59,3,59,6],[54,3,54,6],[55,3,55,6],[44,3,44,6],[45,3,45,6],[46,3,46,6],[47,3,47,6],[42,3,42,6],[43,3,43,6],[32,3,32,6],[33,3,33,6],[34,3,34,6],[35,3,35,6],[30,3,30,6],[31,3,31,6],[20,3,20,6],[21,3,21,6],[22,3,22,6],[23,3,23,6],[19,3,19,6],[9,3,9,6],[10,3,10,6],[11,3,11,6],[12,3,12,6],[6,9,11,9],[37,0,38,2],[35,0,36,2],[39,0,48,2],[50,0,52,2],[54,0,58,2],[60,0,65,2],[68,0,68,2],[69,0,69,2],[70,0,70,2],[71,0,71,2],[6,0,11,2],[12,0,14,2],[15,0,17,2],[18,0,19,2],[20,0,26,2],[27,0,32,2],[66,0,66,2],[67,0,67,2],[59,0,59,2],[49,0,49,2],[33,0,33,2],[34,0,34,2],[4,0,4,2],[5,0,5,2],[69,8,70,8],[50,8,52,8],[54,8,58,8],[60,8,65,8],[53,0,53,2],[35,8,36,8],[37,8,38,8],[39,8,48,8],[18,8,19,8],[20,8,26,8],[27,8,32,8],[6,8,11,8],[12,8,14,8],[15,8,17,8]]}
[null,null,"COMPRESSOR STATION"]
[null,null,"AL-AT N°: "]
[null,null,"Rev : "]
[null,null,"COMPRESSOR STATION VENDOR DOCUMENT INDEX"]
["DOCUMENT",null,null,"CONTENT",null,null,null,"Supplier Reference\nto be filled by the supplier","DATE requested by AL-AT","DATE confirmed by supplier"]
["OFFER"]
["Compressor Charac.",null,null,"  - Datasheets of main equipments (Compressors, motors, heat exchangers, separator, pumps, …)",null,null,null,null,"With Offer"]
[null,null,null,"  - Compressor Performances"]
[null,null,null,"  - Max-Min Speed with associated Flow"]
[null,null,null,"  - Max-Min Admissible Pressures"]
[null,null,null,"  - Max-Min Admissible Temperatures"]
[null,null,null,"  - Utilities and consumables requirements"]
["Drawings",null,null,"  - Preliminary PID / PFD",null,null,null,null,"With Offer"]
[null,null,null,"  - Compressor preliminary drawing (with internals)"]
[null,null,null,"  - Frame Dimensions (general lay-out)"]
["Technical documents",null,null,"  - Standard Operator Manual",null,null,null,null,"With Offer"]
[null,null,null,"  - Performance Guarantee"]
[null,null,null,"  - Compliance matrix to the present specification"]
["Spare parts lists",null,null,"  - For commissioning",null,null,null,null,"With Offer"]
[null,null,null,"  - For 2 years of operation"]
["Utilities",null,null,"  - Electrical Power:  Total and per consumer",null,null,null,null,"With Offer"]
[null,null,null,"  - Cooling Water: Total and per consumer   (He Cooler, Oil Cooler, Motor, Sep. Lube Oil)"]
[null,null,null,"  -   Instrument Air: Other utilities"]
[null,null,null,"  -    Consumables : "]
[null,null,null,"Charcoal, Motor Lubricating Oil, Compressor Lubricating Oil, Chemicals, etc..."]
[null,null,null,"Type, reference, quantity installed and recommended for maintenance"]
[null,null,null,"Vendor to recommend 2 x Lube Oil compatible with operating conditions."]
["Project",null,null,"  - Overall Schedule (engineering, procurement and manufacturing)",null,null,null,null,"With Offer"]
[null,null,null,"  - Project Organization"]
[null,null,null,"  - Vendor List"]
[null,null,null,"  - Preliminary Project and Quality Management plan"]
[null,null,null,"  - Deliverable list and schedule"]
[null,null,null,"  - Procurement Plan"]
["KOM",null,null,null,null,null,null,null,"T0 + 2 Wks"]
["Documents Lists",null,null,"  - Vendor Document Index: Project Documentation List (VDI) with Document Package Organisation. (this file completed)"]
["Drawings",null,null,"  - Preliminary PID"]
[null,null,null,"  - Preliminary General Layout drawing and main interfaces location"]
["Technical Doc",null,null,"  - Process Calculations"]
[null,null,null,"  - Utility Requirements"]
["Project",null,null,"  - Detailed Planning with list of long lead items"]
[null,null,null,"  - Project Quality Plan"]
[null,null,null,"  - Manufacturing and Inspection Plan: Exchangers (MIP)"]
[null,null,null,"  - List of applicable codes and standards"]
[null,null,null,"  - Project Management Plan"]
[null,null,null,"  - Risk Management Plan"]
[null,null,null,"  - Deliverable list and schedule"]
[null,null,null,"  - Procurement Plan and Vendor List"]
[null,null,null,"  - Piping class"]
[null,null,null,"  - Regulation Compliance Documents"]
["MPR",null,null,null,null,null,null,null,"Monthly"]
["Reporting",null,null,"  - Up-Dated Schedule showing difference vs. Original Schedule"]
[null,null,null,"  - Up-Dated VDI (Document List: showing progress)"]
[null,null,null,"  - Pictures, etc…"]
["PDR",null,null,null,null,null,null,null,"T0 + 8 Wks"]
["Drawings",null,null,"  - Detailed PFD: Process Flow Diagram (all operating modes)"]
[null,null,null,"  - Detailed PID: with Pipes Sizes"]
[null,null,null,"  - Preliminary Drawings of Pressure vessels"]
[null,null,null,"  - Drawings Including all dimensions and main interfaces location "]
[null,null,null,"Civil work drawing basic design: Max load generated and footprint"]
["Project ",null,null,"  - List of non conformances and deviation requests"]
["Technical Doc",null,null,"  - Requirement for building and foundations"]
[null,null,null,"  - Preliminary Functional Analysis"]
[null,null,null,"  - Preliminary Alarms & Trips List"]
[null,null,null,"  - Interface List with characteristics"]
[null,null,null,"  - Preliminary I/O List "]
[null,null,null,"  - ORS Design and Sizing Note"]
["Electrical",null,null,"  - Single Line Diagram"]
["Shipment",null,null,"  - Preliminary Bill of lading with Crates Weights and Dimensions."]
["RISKS",null,null,null,null,null,null,null,"T0 + 12 Wks"]
["Risks",null,null,"  - HAZOP Report & Actions List"]